## Sheet1
No | Job Description | Status | Assignee | Deadline
|  |  |  | 2017-09-11 | 2017-10-11 | 2017-11-11 | 13/11/2017 | 15/11/2017 | 16/11/2017 | 19/11/2017 | 20/11/2017 | 2017-10-12 | 17/11/2017
Explorasi Gmaps API
1 | Distance Matrix | on progress | Alpin Jestinera
2 | Marker | on progress | Fadhlan Ariq M
|  | on progress | Wira Kusuma Wardana
3 | Geolocation | on progress | Naufal Waliy H
|  | on progress | Nurindah Yuniarti
4 | Geocoding | on progress | Reza Dwi Kurniawan
|  | on progress | Putri Dian Insani
5 | Route | on progress | Ira Kusnindi
|  | on progress | Gerry Agustian J
6 | Polyline | on progress | Agustina Bau
|  | on progress | Auliya Aqma
7 | Modes Of Transport | on progress | Said Al Fakhri
|  | on progress | Maulana Ibrahim
8 | Map Event | on progress | Mufid Jamaludin
|  | on progress | Agit Prasetya
IntegrasI API
9 | Menyatukan Semua hasil Explorasi |  | Mufid Jamaludin
Wira Kusuma W
Maulana Ibrahim
Mockup
10 | Screen Flow Diagram |  | Faiz Abdussalam
Alpin Jestinera
11 | Wokflow |  | Ira Kusnindi
Agit Prasetya
12 | Balsamic Mockup |  | Faiz Abdussalam
Diana
13 | Use Case Diagram |  | Putri Dian Insani
Agustina Bau
14 | Sequence Diagram |  | Nurindah
Wira Kusuma W
15 | Domain Model |  | Gerry Agustian
Maulana Ibrahim
16 | Class Daigram |  | Mufid Jamaludin
Reza Dwi Kurniawan
DATABASE
17 | Data Informasi |  | Auliya Aqma Dinillah
Putri Dian Insani
18 | Entity Relationship |  | Naufal Muntaaza
Gerry Agustian
20 | Skema Database |  | Fadhlan ariq
Nurindah
IMPLEMENTASI
21 | Coding |  | Team Backend
| Testing |  | Team Analis